## Slide 1
Applied Architectural Technology 2
TIA 1800
Introduction to Estimating and Costing
Dr Kaushal Keraminiyage
PhD, PgCert, FHEA
Queen’s Street Studios
University of Huddersfield

## Slide 2: This Week….
Client’s priorities
The design and construction process
Forecasting costs
Cost planning

## Slide 3
http://costplanner.com.au/wp-content/uploads/2011/11/home-cartoon.jpg

## Slide 4: Client’s priorities

## Slide 5: The design and construction process : importance of cost management
  Different procurement systems
    Separated systems
    Integrated systems
  Construction process management
    RIBA plan of work
    OGC gateway
    Process protocol

## Slide 6: RIBA plan of work in detail
(RIBA, 2007)

## Slide 7: Cost management
Cost of construction needs to be managed properly both within the design phase and the construction phase.
“Cost management” is a function of “cost planning” and “cost controlling” processes
Like in many management systems, what is measured will get managed
Cost planning is generally the process of establishing cost targets
Cost controlling is the process of controlling the project costs within the established target costs
Cost analysis is a record of how cost has been distributed over the elements of the building (prepared after receiving the tender information)

## Slide 8: Pre contract cost management
(Cartlidge, 2009)

## Slide 9: Cost Planning
Came to prominence during 70’s as a result of the demand for a rigorous and accurate pre-contract costing process
Introduced in 1972, Building Bulletin (4), Department of Education and Science
Often follow the standard list of elements developed by BCIS (currently in transition to NRM)

## Slide 10: Cost Planning
(Cartlidge, 2009)

## Slide 11: Cost Significant Elements
BICS standard list – 7 groups of elements and 34 individual elements
Some elements are cost significant elements (e.g. External walls – about 12-20%, Services 15-30%)
More attention to be given to cost significant elements
Do a cross check with cost analysis of similar buildings to check if cost target for each element is in acceptable range.
(Cartlidge, 2009)

## Slide 12: Methods of Preliminary Estimating
Unit Method
Storey Enclosure Unit Method
Superficial Area Method
Elemental Estimating
Parametric Cost Analysis
Approximate Quantities

## Slide 13: Unit Method
Used at very early stages of design
Can be used when purpose or function of building is known
No drawings or specifications
Use published information or experience
Cost per Unit
  Cost per car -Car Parks
  Cost per bed -Hospitals
  Cost per students -Schools

## Slide 14: Unit Method -Advantages & Disadvantages
Very quick and mathematical process is very simple
Easy to understand and remember
Useful method for estimating the initial cost limit or budget
A cost yardstick which can be used by an architect
Difficult to adjust costs for such factors as shape, size, constructional methods, material, finishing etc.

## Slide 15: Superficial Area Method
Cost per m2
Measured to internal face of external walls
Measured over stair wells, internal partitions, columns and the like
Special items should be excluded & added to overall cost calculated

## Slide 16: Advantages
Rapid
Directly related to accommodation
Allows comparison of different designs
Easy to understand and remember
Allows comparison between buildings that differ in size and shape
A cost yardstick - can be used by an architect

## Slide 17: Approximate Quantities
Uses composite items
Composite rates are achieved by combining similar items of an element
Fairly detailed
Depending on the type of building, purpose of estimate, degree of accuracy required level of detail in measurement varies
More accurate but require more details
Require greater levels of calculation
Requires special estimating paper

## Slide 18: Elemental Estimating
Estimate based on a previous elemental analysis of costs
Estimate derived from modifying and updating the costs of the analysis
Adjustments are for variations in Quantity, Quality and Price
Key method of estimating for CP
Estimate forms the basis for a Cost Plan
Requires much time

## Slide 19: Next Week…
  More on various estimation techniques